## MVP Plan
Phase | Task | DurationDays | DependsOn | Start | End
MVP | Set up solution skeleton | 3 |  | 2025-08-25 | 2025-08-27
MVP | Auth integration with OpenIddict | 2 | Set up solution skeleton | 2025-08-28 | 2025-08-29
MVP | DB schema & migrations | 4 | Set up solution skeleton | 2025-08-28 | 2025-08-31
MVP | Workflow Engine v1 | 8 | DB schema & migrations | 2025-09-01 | 2025-09-08
MVP | Dynamic Form Wizard | 7 | DB schema & migrations | 2025-09-01 | 2025-09-07
MVP | Comments & @mentions | 5 | Set up solution skeleton | 2025-08-28 | 2025-09-01
MVP | Task module | 6 | DB schema & migrations | 2025-09-01 | 2025-09-06
MVP | Notifications | 4 | Comments & @mentions | 2025-09-02 | 2025-09-05
MVP | Attachments | 4 | DB schema & migrations | 2025-09-01 | 2025-09-04
MVP | Dashboards | 4 | Workflow Engine v1 | 2025-09-09 | 2025-09-12
MVP | Consultant Request workflow config | 3 | Workflow Engine v1 | 2025-09-09 | 2025-09-11
MVP | ICT Support workflow config | 3 | Workflow Engine v1 | 2025-09-09 | 2025-09-11
MVP | UAT hardening & DoD checks | 5 | Dashboards | 2025-09-13 | 2025-09-17